## Datapower Changes
number | Category | short_description | assignment_group | assigned_to | risk | impact | type | state | cmdb_ci | cab_date | sys_created_on | cab_date_time | u_cab_meeting | close_code | start_date | end_date | work_start | work_end | Split
CHG0488480 | Certificate Renewal/Installation | CN=wsconnectcloud.gsk.com Certificate installation in Prod. | WebServiceSecurityGateway-L2 | Sivasai Nandi |  |  | Normal | Canceled | us6salxpdp2001 |  | 2025-06-25 13:40 | [7 empty] | HCL
CHG0580273 | Services Disable | Systems outage on the Non-Production environment(QA2) for Core Middleware and B2B DataPower | WebServiceSecurityGateway-L2 | Sharmila Veena | High | 1 - High | Normal | Canceled | us6salxpdp2001 |  | 2025-10-13 12:43 |  |  |  | 2025-10-22 18:00 | 2025-10-24 23:59 |  |  | HCL
CHG0492913 | Certificate Renewal/Installation | WSSG - Certificate installation CN=SSLSalesforceCertificateV7 | WebServiceSecurityGateway-L2 | Sivasai Nandi | Low | 3 - Low | Normal | Closed | us6salxudp2001 |  | 2025-07-01 13:21 |  |  | Successful | 2025-07-03 09:00 | 2025-07-08 23:59 | 2025-07-03 09:00 | 2025-07-04 09:18 | HCL
CHG0486120 | Certificate Renewal/Installation | WSSG - Certificate installation CN=SSLSalesforceCertificateV8 | WebServiceSecurityGateway-L2 | Sivasai Nandi | High | 1 - High | Normal | Closed | us6salxpdp2001 | 2025-07-01 | 2025-06-23 16:00 | 2025-07-01 13:00 | GSK Global CAB | Successful | 2025-07-07 16:00 | 2025-07-09 23:59 | 2025-07-07 16:00 | 2025-07-09 18:28 | HCL
CHG0497245 | Services Disable | Due to Systems outage on the Non-Production environment for Core Middleware and B2B DataPower, we are going to do disable the services in non-production environment. | WebServiceSecurityGateway-L2 | Sivasai Nandi | Low | 3 - Low | Normal | Closed | us6salxudp2001 |  | 2025-07-07 14:34 |  |  | Successful | 2025-07-15 17:00 | 2025-07-16 23:59 | 2025-07-15 17:00 | 2025-07-16 17:14 | HCL
CHG0527241 | Certificate Renewal/Installation | Decommissioning of expired certificate from WSSG Datapower in stage environment. | WebServiceSecurityGateway-L2 | Sharmila Veena | Low | 3 - Low | Normal | Closed | us6salxudp2001 |  | 2025-08-12 03:39 |  |  | Successful | 2025-08-20 08:00 | 2025-08-21 23:59 | 2025-08-20 08:00 | 2025-08-21 13:54 | HCL
CHG0532351 | Migration Request | Migrating VSED to SED LDAP setup in WSSG stage RD domain. | WebServiceSecurityGateway-L2 | Sharmila Veena | Low | 3 - Low | Normal | Closed | us6salxudp2001 |  | 2025-08-18 12:01 |  |  | Successful | 2025-08-20 11:30 | 2025-08-21 23:59 | 2025-08-20 11:30 | 2025-08-21 14:16 | HCL
CHG0528280 | Certificate Renewal/Installation | Decommissioning of expired certificate from WSSG Datapower in dev environment. | WebServiceSecurityGateway-L2 | Sharmila Veena | Low | 3 - Low | Normal | Closed | us6salxddp2001 |  | 2025-08-13 05:03 |  |  | Successful | 2025-08-15 08:00 | 2025-08-16 23:59 | 2025-08-15 08:00 | 2025-08-16 12:32 | HCL
CHG0517339 | Services Disable | Due to Systems outage on the Production environment for Core Middleware and B2B DataPower, we are going to do disable the services in production environment. | WebServiceSecurityGateway-L2 | Sharmila Veena | High | 1 - High | Normal | Closed | us6salxpdp2001 | 2025-08-12 | 2025-07-30 13:14 | 2025-08-12 13:00 | GSK Global CAB | Successful | 2025-08-16 16:30 | 2025-08-18 23:29 | 2025-08-16 16:30 | 2025-08-17 06:47 | HCL
CHG0488483 | Certificate Renewal/Installation | WSSG Certificate Renewal CN= rewirecloud.corpnet2.com, CN=esbcloud.corpnet2.com, CN= wsconnectcloud.corpnet2.com Certificates installation in Prod | WebServiceSecurityGateway-L2 | Sivasai Nandi | High | 1 - High | Normal | Closed | us6salxpdp2001 | 2025-07-24 | 2025-06-25 13:50 | 2025-07-24 13:00 | GSK Global CAB | Successful | 2025-07-25 06:00 | 2025-07-31 23:59 | 2025-07-25 06:00 | 2025-07-29 11:41 | HCL
CHG0513825 | Certificate Renewal/Installation | WSSG Certificate Renewal CN=wsconnectcloud.gsk.com, Certificates installation in Prod. | WebServiceSecurityGateway-L2 | Sharmila Veena | High | 1 - High | Normal | Closed | us6salxpdp2001 | 2025-07-31 | 2025-07-25 13:12 | 2025-07-31 13:00 | GSK Global CAB | Successful | 2025-08-08 06:00 | 2025-08-13 23:59 | 2025-08-08 06:00 | 2025-08-11 11:00 | HCL
CHG0507768 | Services Disable | Due to Systems outage on the Non-Production environment for Core Middleware and B2B DataPower, we are going to do disable the services in non-production environment. | WebServiceSecurityGateway-L2 | Sharmila Veena | Low | 3 - Low | Normal | Closed | us6salxudp2001 |  | 2025-07-18 09:49 |  |  | Successful | 2025-07-24 15:00 | 2025-07-25 23:59 | 2025-07-24 15:00 | 2025-07-25 14:31 | HCL
CHG0514979 | Services Disable | Due to Systems outage on the Non-Production environment for Core Middleware and B2B DataPower, we are going to do disable the services in non-production environment. | WebServiceSecurityGateway-L2 | Sharmila Veena | Low | 3 - Low | Normal | Closed | us6salxudp2001 |  | 2025-07-28 08:14 |  |  | Successful | 2025-08-01 16:30 | 2025-08-02 23:59 | 2025-08-01 16:30 | 2025-08-02 05:15 | HCL

## Sheet2
Row Labels | Count of Category
Account Enable/Disable | 52
SFT Upgrade | 9
Certificate Renewal/Installation | 7
Others | 6
Services Disable | 5
Flow Migration | 4
SFT Installation | 3
Cerificate Renewal | 2
Migration Request | 1
Grand Total | 89

## MFT Changes
number | Category | short_description | assignment_group | assigned_to | risk | impact | type | state | cmdb_ci | cab_date | sys_created_on | cab_date_time | u_cab_meeting | close_code | start_date | end_date | work_start | work_end | Split
CHG0526559 | Others | SFT - Inactive User Cleanup Activity | SecureFileTransfer-L2 | Swapna Rekha | Low | 3 - Low | Normal | Canceled | ie1sxlx00337 |  | 2025-08-11 15:58 | [7 empty] | HCL
CHG0576523 | Others | "SFT DevTest DR Drill" | SecureFileTransfer-L2 | Sathendra Nagariya | Low | 3 - Low | Normal | Closed | ie1sxlx00327 |  | 2025-10-08 09:55 |  |  | Successful | 2025-10-10 08:00 | 2025-10-13 23:59 | 2025-10-10 08:00 | 2025-10-13 16:53 | HCL
CHG0588456 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Abdulhannan Khan | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-10-22 01:19 |  |  | Successful | 2025-10-22 01:30 | 2025-10-23 23:59 | 2025-10-22 01:30 | 2025-10-22 02:17 | HCL
CHG0581398 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Abdulhannan Khan | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-10-14 09:04 |  |  | Successful | 2025-10-14 09:15 | 2025-10-15 23:59 | 2025-10-14 09:15 | 2025-10-14 17:03 | HCL
CHG0584598 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Swapna Rekha | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-10-17 05:05 |  |  | Successful | 2025-10-17 11:25 | 2025-10-17 23:23 | 2025-10-17 11:25 | 2025-10-17 12:08 | HCL
CHG0483733 | Flow Migration | SAFETY_PROD domain creation and XML BY EMAIL flows migration to SAFETY_PROD | SecureFileTransfer-L2 | Sathendra Nagariya | High | 1 - High | Normal | Closed | ie1sxlx00337 | 2025-06-24 | 2025-06-19 14:26 | 2025-06-24 13:00 | GSK Global CAB | Successful | 2025-06-25 10:00 | 2025-07-09 23:59 | 2025-06-25 10:00 | 2025-07-09 14:53 | HCL
CHG0481934 | SFT Upgrade | SFT OT Production upgrade activity | SecureFileTransfer-L2 | Sathendra Nagariya | High | 1 - High | Normal | Closed | ie1osawn00880 | 2025-06-19 | 2025-06-17 18:58 | 2025-06-19 13:00 | GSK Global CAB | Successful | 2025-06-23 10:00 | 2025-06-24 23:59 | 2025-06-23 10:00 | 2025-06-23 17:19 | HCL
CHG0475878 | Flow Migration | OASIS test flows migration | SecureFileTransfer-L2 | Srinu Pachava | Low | 3 - Low | Normal | Closed | ie1sxlx00327 |  | 2025-06-10 10:06 |  |  | Successful | 2025-06-12 10:00 | 2025-06-26 23:59 | 2025-06-12 10:00 | 2025-06-25 16:27 | HCL
CHG0499008 | SFT Upgrade | DevTest GA Gateway patch upgrade activity | SecureFileTransfer-L2 | Sathendra Nagariya | Low | 3 - Low | Normal | Closed | ie1sxlx00327 |  | 2025-07-09 03:59 |  |  | Successful | 2025-07-10 11:30 | 2025-07-11 23:59 | 2025-07-10 11:30 | 2025-07-10 14:03 | HCL
CHG0525007 | Flow Migration | OASIS AS2 flow migration to production | SecureFileTransfer-L2 | Sathendra Nagariya | High | 1 - High | Normal | Closed | ie1sxlx00337 | 2025-08-21 | 2025-08-08 12:17 | 2025-08-21 13:00 | GSK Global CAB | Successful | 2025-08-25 11:30 | 2025-09-08 23:59 | 2025-08-25 11:30 | 2025-09-08 15:19 | HCL
CHG0552915 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Swapna Rekha | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-11 03:37 |  |  | Successful | 2025-09-11 15:34 | 2025-09-11 23:59 | 2025-09-11 15:34 | 2025-09-11 15:57 | HCL
CHG0554551 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Abdulhannan Khan | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-12 15:29 |  |  | Successful | 2025-09-12 15:45 | 2025-09-12 23:59 | 2025-09-12 15:36 | 2025-09-12 16:00 | HCL
CHG0539628 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Swapna Rekha | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-08-26 12:39 |  |  | Successful | 2025-08-26 13:00 | 2025-08-26 23:59 | 2025-08-26 13:00 | 2025-08-26 13:38 | HCL
CHG0540180 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Sharmila Veena | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-08-27 01:28 |  |  | Successful | 2025-08-27 01:45 | 2025-08-28 23:59 | 2025-08-27 01:45 | 2025-08-27 02:39 | HCL
CHG0540634 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Ashish Lal | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-08-27 13:32 |  |  | Successful | 2025-08-27 13:52 | 2025-08-27 23:59 | 2025-08-27 13:52 | 2025-08-27 14:28 | HCL
CHG0540727 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Sharmila Veena | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-08-27 16:43 |  |  | Successful | 2025-08-27 16:45 | 2025-08-28 23:59 | 2025-08-27 16:45 | 2025-08-27 16:59 | HCL
CHG0541530 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Swapna Rekha | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-08-28 10:53 |  |  | Successful | 2025-08-28 10:56 | 2025-08-28 23:54 | 2025-08-28 10:56 | 2025-08-28 11:16 | HCL
CHG0541599 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Swapna Rekha | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-08-28 12:17 |  |  | Successful | 2025-08-28 12:40 | 2025-08-28 23:59 | 2025-08-28 12:40 | 2025-08-28 13:03 | HCL
CHG0541709 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Abdulhannan Khan | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-08-28 14:42 |  |  | Successful | 2025-08-28 14:48 | 2025-08-28 23:59 | 2025-08-28 14:48 | 2025-08-28 15:24 | HCL
CHG0546229 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Abdulhannan Khan | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-03 09:48 |  |  | Successful | 2025-09-03 09:55 | 2025-09-04 23:59 | 2025-09-03 09:55 | 2025-09-04 16:08 | HCL
CHG0547676 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Sharmila Veena | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-04 16:12 |  |  | Successful | 2025-09-04 16:15 | 2025-09-05 23:59 | 2025-09-04 16:15 | 2025-09-05 10:32 | HCL
CHG0536629 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Sivasai Nandi | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-08-22 09:44 |  |  | Successful | 2025-08-22 10:30 | 2025-08-22 23:59 | 2025-08-22 10:30 | 2025-08-22 11:03 | HCL
CHG0536711 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Swapna Rekha | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-08-22 11:18 |  |  | Successful | 2025-08-22 11:30 | 2025-08-22 23:59 | 2025-08-22 11:30 | 2025-08-22 12:03 | HCL
CHG0538230 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Sivasai Nandi | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-08-25 10:54 |  |  | Successful | 2025-08-25 11:30 | 2025-08-25 23:59 | 2025-08-25 11:30 | 2025-08-25 12:14 | HCL
CHG0538374 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Swapna Rekha | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-08-25 14:15 |  |  | Successful | 2025-08-25 15:00 | 2025-08-25 23:59 | 2025-08-25 15:00 | 2025-08-25 16:32 | HCL
CHG0535572 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Sharmila Veena | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-08-21 09:55 |  |  | Successful | 2025-08-21 10:15 | 2025-08-22 23:59 | 2025-08-21 10:15 | 2025-08-21 12:23 | HCL
CHG0550027 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Sivasai Nandi | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-08 14:15 |  |  | Successful | 2025-09-08 14:30 | 2025-09-08 23:59 | 2025-09-08 14:30 | 2025-09-08 15:21 | HCL
CHG0548471 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Swapna Rekha | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-05 11:43 |  |  | Successful | 2025-09-05 13:47 | 2025-09-08 23:59 | 2025-09-05 13:47 | 2025-09-08 17:28 | HCL
CHG0551181 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Sivasai Nandi | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-09 10:05 |  |  | Successful | 2025-09-09 10:30 | 2025-09-09 23:59 | 2025-09-09 10:30 | 2025-09-09 11:01 | HCL
CHG0551456 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Abdulhannan Khan | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-09 16:07 |  |  | Successful | 2025-09-09 16:10 | 2025-09-09 23:59 | 2025-09-09 16:10 | 2025-09-09 16:30 | HCL
CHG0552335 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Abdulhannan Khan | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-10 12:55 |  |  | Successful | 2025-09-10 12:59 | 2025-09-10 23:59 | 2025-09-10 12:59 | 2025-09-10 13:58 | HCL
CHG0543952 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Swapna Rekha | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-01 08:29 |  |  | Successful | 2025-09-01 08:33 | 2025-09-01 23:59 | 2025-09-01 08:33 | 2025-09-01 14:22 | HCL
CHG0544240 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Ashish Lal | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-01 15:41 |  |  | Successful | 2025-09-01 15:50 | 2025-09-01 23:59 | 2025-09-01 15:50 | 2025-09-01 16:35 | HCL
CHG0545402 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Sharmila Veena | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-02 13:28 |  |  | Successful | 2025-09-02 13:33 | 2025-09-03 23:59 | 2025-09-02 13:33 | 2025-09-02 14:00 | HCL
CHG0462530 | SFT Upgrade | SFT IT DevTest & SFT OT TEST Upgrade | SecureFileTransfer-L2 | Sathendra Nagariya | Low | 3 - Low | Normal | Closed | ie1sxlx00327 |  | 2025-05-23 13:18 |  |  | Successful | 2025-05-30 09:00 | 2025-06-02 23:59 | 2025-05-30 09:00 | 2025-06-02 19:08 | HCL
CHG0455487 | Others | SFT -DEVTEST- SAFETY_TEST Domain Configuration & XML by Email, AS2 & SFTP Project configuration to new Domain "SAFETY _DEV" | SecureFileTransfer-L2 | Sathendra Nagariya | Low | 3 - Low | Normal | Closed | ie1sxlx00327 |  | 2025-05-14 08:57 |  |  | Successful with issues | 2025-05-21 09:32 | 2025-06-10 09:32 | 2025-05-21 09:32 | 2025-06-10 11:48 | HCL
CHG0462538 | SFT Upgrade | SFT IT Production Upgrade and configuration changes for Healthcheck Paramaeter Implementation | SecureFileTransfer-L2 | Sathendra Nagariya | High | 1 - High | Normal | Closed | ie1sxlx00337 | 2025-06-05 | 2025-05-23 13:20 | 2025-06-05 13:00 | GSK Global CAB | Successful | 2025-06-07 06:30 | 2025-06-13 23:59 | 2025-06-07 06:30 | 2025-06-13 16:03 | HCL
CHG0474650 | SFT Installation | Opswat OT AV installation | SecureFileTransfer-L2 | Sathendra Nagariya | High | 1 - High | Normal | Closed | ie1osawn00886 | 2025-06-12 | 2025-06-09 12:19 | 2025-06-12 13:00 | GSK Global CAB | Successful | 2025-06-13 11:00 | 2025-06-20 23:59 | 2025-06-13 11:00 | 2025-06-16 16:15 | HCL
CHG0450975 | Others | SFT -DEVTEST- Domain Configuration & XML by Email, AS2 & SFTP Project configuration to new Domain "SAFETY _DEV" | SecureFileTransfer-L2 | Palaniyappan Ramaswamy | Low | 3 - Low | Normal | Closed | ie1sxlx00327 |  | 2025-05-07 11:07 |  |  | Successful | 2025-05-14 09:00 | 2025-05-21 23:59 | 2025-05-14 09:00 | 2025-05-21 13:28 | HCL
CHG0439685 | SFT Installation | SFT OT production Installation | SecureFileTransfer-L2 | Sathendra Nagariya | High | 1 - High | Normal | Closed | ie1osawn00881 | 2025-04-15 | 2025-04-10 13:50 | 2025-04-15 13:00 | GSK Global CAB | Successful | 2025-04-17 15:00 | 2025-04-30 23:59 | 2025-04-17 15:00 | 2025-04-25 13:22 | HCL
CHG0576387 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Sharmila Veena | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-10-08 06:54 |  |  | Successful | 2025-10-08 09:30 | 2025-10-09 23:59 | 2025-10-08 09:30 | 2025-10-08 10:18 | HCL
CHG0571670 | SFT Upgrade | SFT OT Prod upgrade | SecureFileTransfer-L2 | Sathendra Nagariya | High | 1 - High | Normal | Closed | ie1osawn00880 | 2025-10-07 | 2025-10-02 08:08 | 2025-10-07 13:00 | GSK Global CAB | Successful | 2025-10-08 11:00 | 2025-10-10 23:59 | 2025-10-08 11:00 | 2025-10-08 19:55 | HCL
CHG0577408 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Sharmila Veena | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-10-09 05:26 |  |  | Successful | 2025-10-09 09:30 | 2025-10-10 23:59 | 2025-10-09 09:30 | 2025-10-09 13:04 | HCL
CHG0578711 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Swapna Rekha | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-10-10 09:28 |  |  | Successful | 2025-10-10 15:31 | 2025-10-10 23:30 | 2025-10-10 15:31 | 2025-10-10 15:58 | HCL
CHG0569718 | Cerificate Renewal | AS2 partner certificate installation | SecureFileTransfer-L2 | Sathendra Nagariya | High | 1 - High | Normal | Closed | ie1sxlx00337 | 2025-10-02 | 2025-09-30 08:40 | 2025-10-02 13:00 | GSK Global CAB | Successful | 2025-10-03 11:00 | 2025-10-06 23:59 | 2025-10-03 11:00 | 2025-10-06 15:04 | HCL
CHG0564766 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Abdulhannan Khan | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-24 08:22 |  |  | Successful | 2025-09-24 08:45 | 2025-09-24 23:59 | 2025-09-24 08:41 | 2025-09-24 09:42 | HCL
CHG0565044 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Ashish Lal | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-24 14:47 |  |  | Successful | 2025-09-24 15:18 | 2025-09-25 23:59 | 2025-09-24 15:18 | 2025-09-25 12:40 | HCL
CHG0570793 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Gyanendra Mishra | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-10-01 10:31 |  |  | Successful | 2025-10-01 10:45 | 2025-10-02 23:59 | 2025-10-01 10:45 | 2025-10-01 11:57 | HCL
CHG0570892 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Swapna Rekha | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-10-01 13:05 |  |  | Successful | 2025-10-01 13:10 | 2025-10-01 23:50 | 2025-10-01 13:10 | 2025-10-01 15:27 | HCL
CHG0571655 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Gyanendra Mishra | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-10-02 08:03 |  |  | Successful | 2025-10-02 08:15 | 2025-10-03 23:59 | 2025-10-02 08:15 | 2025-10-02 08:38 | HCL
CHG0571845 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Abdulhannan Khan | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-10-02 16:10 |  |  | Successful | 2025-10-02 16:15 | 2025-10-03 23:59 | 2025-10-02 16:15 | 2025-10-03 08:17 | HCL
CHG0572539 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Ashish Lal | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-10-03 08:11 |  |  | Successful | 2025-10-03 13:45 | 2025-10-03 23:59 | 2025-10-03 13:45 | 2025-10-03 14:44 | HCL
CHG0571672 | SFT Upgrade | SFT OT Preprod upgrade | SecureFileTransfer-L2 | Sathendra Nagariya | Low | 3 - Low | Normal | Closed | ie1osawn00801 |  | 2025-10-02 08:14 |  |  | Successful | 2025-10-03 13:00 | 2025-10-06 23:59 | 2025-10-03 13:00 | 2025-10-03 17:08 | HCL
CHG0559994 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Sivasai Nandi | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-18 09:58 |  |  | Successful | 2025-09-18 10:35 | 2025-09-18 23:59 | 2025-09-18 10:35 | 2025-09-18 11:06 | HCL
CHG0560101 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Ashish Lal | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-18 13:29 |  |  | Successful | 2025-09-19 09:00 | 2025-09-19 23:59 | 2025-09-19 09:01 | 2025-09-19 15:15 | HCL
CHG0561251 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Swapna Rekha | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-19 15:23 |  |  | Successful | 2025-09-19 15:30 | 2025-09-19 23:29 | 2025-09-19 15:30 | 2025-09-19 15:49 | HCL
CHG0560078 | SFT Upgrade | SFT IT Production Upgrade activity | SecureFileTransfer-L2 | Sathendra Nagariya | High | 1 - High | Normal | Closed | ie1sxlx00337 | 2025-09-18 | 2025-09-18 12:36 | 2025-09-18 13:00 | GSK Global CAB | Successful | 2025-09-20 06:00 | 2025-09-22 23:59 | 2025-09-20 06:00 | 2025-09-22 08:45 | HCL
CHG0562429 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Abdulhannan Khan | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-22 09:02 |  |  | Successful | 2025-09-22 10:00 | 2025-09-22 23:59 | 2025-09-22 10:00 | 2025-09-22 11:35 | HCL
CHG0548491 | SFT Upgrade | SFT DevTest upgrade | SecureFileTransfer-L2 | Sathendra Nagariya | Low | 3 - Low | Normal | Closed | ie1sxlx00327 |  | 2025-09-05 12:08 |  |  | Successful | 2025-09-09 11:30 | 2025-09-12 23:59 | 2025-09-09 11:30 | 2025-09-11 09:17 | HCL
CHG0556303 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Ashish Lal | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-15 08:15 |  |  | Successful | 2025-09-15 08:40 | 2025-09-15 23:59 | 2025-09-15 08:40 | 2025-09-15 14:48 | HCL
CHG0557769 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Swapna Rekha | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-16 10:50 |  |  | Successful | 2025-09-16 10:55 | 2025-09-16 23:53 | 2025-09-16 10:55 | 2025-09-16 14:55 | HCL
CHG0558870 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Swapna Rekha | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-17 10:19 |  |  | Successful | 2025-09-17 10:34 | 2025-09-17 23:33 | 2025-09-17 10:34 | 2025-09-17 16:01 | HCL
CHG0562716 | Others | Production SFT syslog update with CRIBL | SecureFileTransfer-L2 | Sathendra Nagariya | High | 1 - High | Normal | Closed | ie1sxlx00337 | 2025-09-25 | 2025-09-22 15:20 | 2025-09-25 13:00 | GSK Global CAB | Successful | 2025-09-26 11:00 | 2025-09-30 23:59 | 2025-09-26 11:00 | 2025-09-26 14:05 | HCL
CHG0573885 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Ashish Lal | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-10-06 07:33 |  |  | Successful | 2025-10-06 13:05 | 2025-10-06 23:59 | 2025-10-06 13:05 | 2025-10-06 13:35 | HCL
CHG0575666 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Swapna Rekha | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-10-07 14:35 |  |  | Successful | 2025-10-07 16:43 | 2025-10-07 23:42 | 2025-10-07 16:43 | 2025-10-07 17:26 | HCL
CHG0566192 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Sivasai Nandi | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-25 15:21 |  |  | Successful | 2025-09-25 15:30 | 2025-09-26 23:59 | 2025-09-25 15:30 | 2025-09-26 13:01 | HCL
CHG0563878 | Others | Opswat ICAP - production release | SecureFileTransfer-L2 | Sathendra Nagariya | High | 1 - High | Normal | Closed | ie1osawn00886 | 2025-09-25 | 2025-09-23 12:34 | 2025-09-25 13:00 | GSK Global CAB | Successful | 2025-09-26 12:36 | 2025-10-03 12:36 | 2025-09-26 12:36 | 2025-09-26 13:17 | HCL
CHG0568535 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Ashish Lal | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-29 10:36 |  |  | Successful | 2025-09-29 10:46 | 2025-09-29 23:59 | 2025-09-29 10:46 | 2025-09-29 13:35 | HCL
CHG0568717 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT GA | SecureFileTransfer-L2 | Abdulhannan Khan | Low | 3 - Low | Standard | Closed | ie1sxlx00337 |  | 2025-09-29 15:14 |  |  | Successful | 2025-09-29 15:30 | 2025-09-30 23:59 | 2025-09-29 15:30 | 2025-09-29 15:45 | HCL
CHG0517357 | SFT Installation | DR GA MFT and DR Gateway Preprod-Informal installation | SecureFileTransfer-L2 | Sathendra Nagariya | Low | 3 - Low | Normal | Closed | nl1sxlx00024 |  | 2025-07-30 13:40 |  |  | Successful | 2025-09-17 10:00 | 2025-09-29 23:59 | 2025-09-17 10:00 | 2025-09-29 17:55 | HCL
CHG0507953 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT prod servers | SecureFileTransfer-L2 | Sharmila Veena | High | 1 - High | Normal | Closed | ie1sxlx00337 | 2025-08-14 | 2025-07-18 14:36 | 2025-08-14 13:00 | GSK Global CAB | Successful | 2025-08-16 04:30 | 2025-08-17 23:59 | 2025-08-16 04:30 | 2025-08-16 06:25 | HCL
CHG0520895 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT prod servers | SecureFileTransfer-L2 | Sharmila Veena | High | 1 - High | Normal | Closed | ie1sxlx00337 | 2025-08-14 | 2025-08-04 17:58 | 2025-08-14 13:00 | GSK Global CAB | Successful | 2025-08-15 09:30 | 2025-08-16 23:59 | 2025-08-15 09:30 | 2025-08-15 14:49 | HCL
CHG0520894 | Account Enable/Disable | SFT User account enabled and disabled activity in SFT prod servers | SecureFileTransfer-L2 | Sharmila Veena | High | 1 - High | Normal | Closed | ie1sxlx00337 | 2025-08-14 | 2025-08-04 17:54 | 2025-08-14 13:00 | GSK Global CAB | Successful | 2025-08-16 05:30 | 2025-08-17 23:59 | 2025-08-16 05:30 | 2025-08-16 06:03 | HCL
CHG0501515 | SFT Upgrade | GA Gateway production upgrade | SecureFileTransfer-L2 | Sathendra Nagariya | High | 1 - High | Normal | Closed | ie1sxlx00337 | 2025-07-15 | 2025-07-11 13:26 | 2025-07-15 13:00 | GSK Global CAB | Successful | 2025-07-19 06:00 | 2025-07-21 23:59 | 2025-07-19 06:00 | 2025-07-20 06:37 | HCL
CHG0517185 | Flow Migration | OASIS SFTP and XML BY EMAIL flows migration to Production | SecureFileTransfer-L2 | Sathendra Nagariya | High | 1 - High | Normal | Closed | ie1sxlx00337 | 2025-08-05 | 2025-07-30 09:45 | 2025-08-05 13:00 | GSK Global CAB | Successful | 2025-08-06 10:30 | 2025-08-13 23:59 | 2025-08-06 10:30 | 2025-08-08 16:27 | HCL
CHG0510669 | Cerificate Renewal | Production SFT China upgrade and cert renewal. | SecureFileTransfer-L2 | Sathendra Nagariya | High | 1 - High | Normal | Closed | cn1sxlx00132 | 2025-07-31 | 2025-07-22 12:08 | 2025-07-31 13:00 | GSK Global CAB | Successful | 2025-08-02 05:30 | 2025-08-05 23:59 | 2025-08-02 05:30 | 2025-08-02 10:40 | HCL
CHG0488480 | Certificate Renewal/Installation | CN=wsconnectcloud.gsk.com Certificate installation in Prod. | WebServiceSecurityGateway-L2 | Sivasai Nandi |  |  | Normal | Canceled | us6salxpdp2001 |  | 2025-06-25 13:40 | [7 empty] | HCL
CHG0580273 | Services Disable | Systems outage on the Non-Production environment(QA2) for Core Middleware and B2B DataPower | WebServiceSecurityGateway-L2 | Sharmila Veena | High | 1 - High | Normal | Canceled | us6salxpdp2001 |  | 2025-10-13 12:43 |  |  |  | 2025-10-22 18:00 | 2025-10-24 23:59 |  |  | HCL
CHG0492913 | Certificate Renewal/Installation | WSSG - Certificate installation CN=SSLSalesforceCertificateV7 | WebServiceSecurityGateway-L2 | Sivasai Nandi | Low | 3 - Low | Normal | Closed | us6salxudp2001 |  | 2025-07-01 13:21 |  |  | Successful | 2025-07-03 09:00 | 2025-07-08 23:59 | 2025-07-03 09:00 | 2025-07-04 09:18 | HCL
CHG0486120 | Certificate Renewal/Installation | WSSG - Certificate installation CN=SSLSalesforceCertificateV8 | WebServiceSecurityGateway-L2 | Sivasai Nandi | High | 1 - High | Normal | Closed | us6salxpdp2001 | 2025-07-01 | 2025-06-23 16:00 | 2025-07-01 13:00 | GSK Global CAB | Successful | 2025-07-07 16:00 | 2025-07-09 23:59 | 2025-07-07 16:00 | 2025-07-09 18:28 | HCL
CHG0497245 | Services Disable | Due to Systems outage on the Non-Production environment for Core Middleware and B2B DataPower, we are going to do disable the services in non-production environment. | WebServiceSecurityGateway-L2 | Sivasai Nandi | Low | 3 - Low | Normal | Closed | us6salxudp2001 |  | 2025-07-07 14:34 |  |  | Successful | 2025-07-15 17:00 | 2025-07-16 23:59 | 2025-07-15 17:00 | 2025-07-16 17:14 | HCL
CHG0527241 | Certificate Renewal/Installation | Decommissioning of expired certificate from WSSG Datapower in stage environment. | WebServiceSecurityGateway-L2 | Sharmila Veena | Low | 3 - Low | Normal | Closed | us6salxudp2001 |  | 2025-08-12 03:39 |  |  | Successful | 2025-08-20 08:00 | 2025-08-21 23:59 | 2025-08-20 08:00 | 2025-08-21 13:54 | HCL
CHG0532351 | Migration Request | Migrating VSED to SED LDAP setup in WSSG stage RD domain. | WebServiceSecurityGateway-L2 | Sharmila Veena | Low | 3 - Low | Normal | Closed | us6salxudp2001 |  | 2025-08-18 12:01 |  |  | Successful | 2025-08-20 11:30 | 2025-08-21 23:59 | 2025-08-20 11:30 | 2025-08-21 14:16 | HCL
CHG0528280 | Certificate Renewal/Installation | Decommissioning of expired certificate from WSSG Datapower in dev environment. | WebServiceSecurityGateway-L2 | Sharmila Veena | Low | 3 - Low | Normal | Closed | us6salxddp2001 |  | 2025-08-13 05:03 |  |  | Successful | 2025-08-15 08:00 | 2025-08-16 23:59 | 2025-08-15 08:00 | 2025-08-16 12:32 | HCL
CHG0517339 | Services Disable | Due to Systems outage on the Production environment for Core Middleware and B2B DataPower, we are going to do disable the services in production environment. | WebServiceSecurityGateway-L2 | Sharmila Veena | High | 1 - High | Normal | Closed | us6salxpdp2001 | 2025-08-12 | 2025-07-30 13:14 | 2025-08-12 13:00 | GSK Global CAB | Successful | 2025-08-16 16:30 | 2025-08-18 23:29 | 2025-08-16 16:30 | 2025-08-17 06:47 | HCL
CHG0488483 | Certificate Renewal/Installation | WSSG Certificate Renewal CN= rewirecloud.corpnet2.com, CN=esbcloud.corpnet2.com, CN= wsconnectcloud.corpnet2.com Certificates installation in Prod | WebServiceSecurityGateway-L2 | Sivasai Nandi | High | 1 - High | Normal | Closed | us6salxpdp2001 | 2025-07-24 | 2025-06-25 13:50 | 2025-07-24 13:00 | GSK Global CAB | Successful | 2025-07-25 06:00 | 2025-07-31 23:59 | 2025-07-25 06:00 | 2025-07-29 11:41 | HCL
CHG0513825 | Certificate Renewal/Installation | WSSG Certificate Renewal CN=wsconnectcloud.gsk.com, Certificates installation in Prod. | WebServiceSecurityGateway-L2 | Sharmila Veena | High | 1 - High | Normal | Closed | us6salxpdp2001 | 2025-07-31 | 2025-07-25 13:12 | 2025-07-31 13:00 | GSK Global CAB | Successful | 2025-08-08 06:00 | 2025-08-13 23:59 | 2025-08-08 06:00 | 2025-08-11 11:00 | HCL
CHG0507768 | Services Disable | Due to Systems outage on the Non-Production environment for Core Middleware and B2B DataPower, we are going to do disable the services in non-production environment. | WebServiceSecurityGateway-L2 | Sharmila Veena | Low | 3 - Low | Normal | Closed | us6salxudp2001 |  | 2025-07-18 09:49 |  |  | Successful | 2025-07-24 15:00 | 2025-07-25 23:59 | 2025-07-24 15:00 | 2025-07-25 14:31 | HCL
CHG0514979 | Services Disable | Due to Systems outage on the Non-Production environment for Core Middleware and B2B DataPower, we are going to do disable the services in non-production environment. | WebServiceSecurityGateway-L2 | Sharmila Veena | Low | 3 - Low | Normal | Closed | us6salxudp2001 |  | 2025-07-28 08:14 |  |  | Successful | 2025-08-01 16:30 | 2025-08-02 23:59 | 2025-08-01 16:30 | 2025-08-02 05:15 | HCL